## Sheet1
Project Timeline |  | *note, use iterative process flow in the book
Time | 2670 hours | 500 days | 100 weeks | 25 months
Starting date | 2017-01-10
Deadline date | 2019-01-28
Strategy | Iterative, Spiral
| Month |  | 1 | 2 | 3 | 4 | 5 |  |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Project Planning | [7 empty] | a | b | bar: 6 to 11
Research
Analysis
Design | bar: 6 to 9
Prototype | bar: 10 to 11
Development | bar: 12 to 23
Foundation | bar: 12 to 15
API
Enrollment management
Data storage
GUI/User access
Generalization | bar: 16 to 18
Functional | bar: 19 to 20
Non-Functional | bar: 21 to 23
Testing | bar: 15; 18; 20; 23 to 25
| Date |  | 2017-01-10 |  | 2017-03-11 |  | 2017-05-10 |  |  | 10: 2017-10-07; 12: 2017-12-05; 16: 2018-04-04; 19: 2018-07-03; 21: 2018-09-01; 24: 2018-11-29
| Cases | [8 empty] | 15: Best 3/6/18; 25: Average 1/28/19
Finish Dates
| Best |  | 2018-03-06
| Average |  | 2019-01-28
| Worst |  | 2019-04-30
Definitions
| Research |  | Research necessary ideas, strategies and informations required for the project
| Analysis |  | See or make sense of how the project will work
| Design |  | Plan how to achieve it and and how the look and the functionality of the project
| Prototype |  | Make a preliminary model of the project
| Foundation |  | Create the underlying basis or principle of the project
| Generalization |  | Create reusable classes, methods and functionality that are appropriate to the requirements
| Functional |  | Develop necessary behaviors regarding the requirements
| Non-Functional |  | Develop the project's structure and non-functionality/ implement necessary hardwares that satisfy the requirements
| Testing |  | Test for bugs and errors