## Sheet2
Project Timeline
Time | 1800 hours
40 hours a week | ~45 weeks
~11.5 months
Starting date | 2017-01-10
Deadline date | 2017-11-26
Strategy | Iterative, Spiral
|  | date |  | 2016-01-24 | 2016-02-07 | 2016-02-21 | 2016-03-07 | 2016-03-21 | 2016-04-04 | 2016-04-17 | 2016-05-01 | 2016-05-15 |  | 2016-05-29 |  | 2016-06-12 | 2016-06-26 |  | 2016-07-10 |  | 2016-07-24 | 2016-08-07 | 2016-08-21 | 2016-09-04 | 2016-09-18 | 2016-10-02 |  | 2016-10-16 |  | 2016-10-30 | 2016-11-12 |  | 2016-11-26
Name | Phase | week |  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 |  | 20 |  | 22 | 24 |  | 26 |  | 28 | 30 | 32 | 34 | 36 | 38 |  | 40 |  | 42 | 44 |  | 46
API (18 weeks, ~4 months) |  |  | API
| Communication |  | 0.5
| Planning |  |  | 2016-01-24: 1.5; 2016-02-07: 2; 2016-02-21: 2
| Modeling |  |  | 2016-03-07: 2; 2016-03-21: 2
| Construction |  |  | 2016-04-04: 2; 2016-04-17: 2; 2016-05-01: 2
| Deployment |  |  | 2016-05-15: 2
Enrollment Management (8 weeks, 2 months) | [12 empty] | Enrollment Management
| Communication | [11 empty] | 0.3
| Planning | [12 empty] | 1.7 | 1
| Modeling | [14 empty] | 1
| Construction | [15 empty] | 2 | 1
| Deployment | [17 empty] | 1
Data Storage (12 weeks, 3 months) | [19 empty] | Data Storage
| Communication | [18 empty] | 0.5
| Planning | [19 empty] | 1.5 | 2
| Modeling | [21 empty] | 2
| Construction | [22 empty] | 2 | 2
| Deployment | [24 empty] | 2
GUI/User (8 weeks, 2 months) | [26 empty] | GUI/User
| Communication | [25 empty] | 0.3
| Planning | [26 empty] | 1.7 | 1
| Modeling | [28 empty] | 1
| Construction | [29 empty] | 2 | 1
| Deployment | [31 empty] | 1